## Delivery Timeline
AAM Delivery Plan: November 2026 to February 2027
Start | 2026-11-02T00:00:00.000Z |  | Deadline | 2027-02-26T00:00:00.000Z | Go-live | 2027-02-23T00:00:00.000Z |  |  | Care ends | 2027-02-26 |  |  | Fits deadline
Dev 1: API and Portal. Dev 2: Worker, PostgreSQL and Azure. Both own CI/CD, replicas and observability for their services.
Lunar New Year leave: Feb 3–12. Dec 25–Jan 1 is scheduled for delivery, testing and tuning. Full re-entry regression precedes release.
Scheduled labor | 107640 |  | Person-days | 299 | Workdays | 77 |  | per person after holidays; labor cost excludes reserve, Azure and model usage.
ID | Delivery workstream | Lead | Start | Finish | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17
[5 empty] | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22
| Available workdays |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5
P01 | API/Portal foundation and user access | Dev 1 | 2026-11-02 | 2026-11-13 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02 | Worker, database and Azure foundation | Dev 2 | 2026-11-02 | 2026-11-27 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P03 | Case, Open Items and Triage | Dev 1 | 2026-11-16 | 2026-12-04 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P04 | Draft, approve and automatic send | Dev 1 | 2026-11-30 | 2026-12-18 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P05 | Customer and Regional/Local overview | Dev 1 | 2026-12-14 | 2026-12-18 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P06 | Prompt/example-driven Playbook Studio | DS | 2026-12-14 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P07 | CI/CD, replicas and observability | Both Devs | 2026-12-21 | 2027-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P08 | Corpus, labels and model baseline | DS | 2026-11-02 | 2026-11-20 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P09 | Prompt, schema and Playbook tuning | DS | 2026-11-23 | 2027-01-08 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P10 | Continuous technical automation | Tester 1 | 2026-11-02 | 2027-01-01 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P11 | Continuous business acceptance | Tester 2 | 2026-11-16 | 2027-01-08 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12 | System, HA and recovery qualification | Tester 1 | 2027-01-04 | 2027-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
P13 | Independent frozen-candidate evaluation | Tester 2 | 2027-01-11 | 2027-01-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
P14 | Pilot AM UAT, fixes and acceptance | Tester 2 | 2027-01-18 | 2027-01-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
P15 | Pre-holiday release checkpoint | Dev 1 | 2027-02-01 | 2027-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
P16 | Post-holiday full regression and readiness | Tester 1 | 2027-02-15 | 2027-02-19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
P17 | Production rollout and care | Dev 2 | 2027-02-22 | 2027-02-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Milestones and release gates
Gate | Milestone | Accountable | Review date | Evidence
G1 | Identity and platform connected | Dev 2 | 2026-11-13 | Not run | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2 | Real-mail Triage working | Dev 2 | 2026-12-04 | Not run | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3 | Approve-and-send end to end | Dev 1 | 2026-12-11 | Not run | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4 | Launch features frozen | Dev 1 | 2027-01-01 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5 | Independent evaluation / RC | DS | 2027-01-15 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
G6 | Pilot UAT accepted | Tester 2 | 2027-01-29 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
G7 | Pre-holiday release checkpoint | Dev 1 | 2027-02-02 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
G8 | Post-holiday Go / No-Go | Tester 1 | 2027-02-19 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
G9 | Production release | Dev 2 | 2027-02-23 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G10 | Care and handover complete | Dev 1 | 2027-02-26 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Holiday columns are grey. Feb 1 has 2 workdays. Dec 21–Jan 1 has 10 workdays for delivery, testing and tuning.
Key dates: feature freeze Jan 1; independent evaluation Jan 15; UAT Jan 29; pre-break freeze Feb 2; re-entry gate Feb 19.
Go-live is proposed for Feb 23, with care through Feb 26. Dates move with the working calendar; the deadline stays fixed.
Cost uses allocated person-days shown in the detailed Gantt, not the full task window or total payroll availability.

## Task Plan
Task Ownership, Working-Day Gantt and Labor Cost
Yellow cells are editable. Gantt cells show scheduled person-days. EXT = external dependency, not estimated or costed.
Start WD / Window WD use the holiday-adjusted workday index. :SS = same-window integration; otherwise finish-to-start. Capacity is not automatically leveled.
ID | Workstream | Task / deliverable | Owner | Dependencies | Start WD | Window WD | Effort days | Finish WD | Start date | Finish date | Progress | Plan check | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | Cost (USD) | Exit criteria / evidence | Handoff / scope notes
[13 empty] | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22
A01 | Worker / Azure | Worker skeleton, PostgreSQL migrations and CI | Dev 2 |  | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Worker deploys independently; schema migration and Worker CI pass.
A02 | Worker / Azure | Entra connection, token cache and Azure access | Dev 2 | A01, E01 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Graph renewal and Foundry smoke call work; secrets stay outside code.
A03 | Worker / Azure | Inbox / Sent Items delta synchronization | Dev 2 | A02 | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Pagination, immutable IDs, duplicates and cursor recovery are verified.
A04 | Worker / Azure | Persistent jobs, leases and Spring AI adapter | Dev 2 | A03, S03 | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Atomic job claims, stale-result rejection and typed Foundry responses work.
A05 | Worker / Azure | Intake and Case-matching orchestration | Dev 2 | A04, B04, S04 | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Real test mail produces traceable Create / Link / Ignore proposals.
A06 | Worker / Azure | Graph sending after AM approval | Dev 2 | A05, B05 | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Approved content is persisted before send; duplicate approval cannot resend.
A07 | Worker / Azure | Uncertain sends and Sent Items reconciliation | Dev 2 | A06 | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Lost responses and delayed sent copies reconcile without blind retries.
A08 | Worker / Azure | Worker replicas, backlog telemetry and alerts | Dev 2 | A07 | 36 | 10 | 8 | 45 | 2026-12-21 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | Worker scaling, lease expiry, sync lag and dependency alerts are observable. | Dec 21–Jan 1: implementation, load checks and fault-finding fixes.
A09 | Worker / Azure | Concurrency, JVM loss and database failover fixes | Dev 2 | A08, Q08 | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Restart, duplicate work and stale-worker fault findings are closed.
A10 | Worker / Azure | Preproduction, backups and deployment recovery | Dev 2 | A09, E03 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Clean deployment, DB/Blob restore and provider quotas are qualified.
A11 | Worker / Azure | UAT integration fixes and sender retesting | Dev 2 | A10 | 56 | 5 | 4 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1440 | Integration issues are closed and impacted send/recovery paths retested.
A12 | Worker / Azure | Release branch and Worker rollback rehearsal | Dev 2 | A11, Q11 | 61 | 5 | 4 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1440 | Worker rollout, fencing and rollback runbook have execution evidence.
A13 | Worker / Azure | Pre-holiday deployment and recovery checkpoint | Dev 2 | A12, Q12 | 66 | 2 | 1.5 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 540 | Backups, queued work and approved artifacts are checked before leave. | Only Feb 1–2 are working days.
A14 | Worker / Azure | Post-holiday environment and integration recovery | Dev 2 | A13 | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1440 | Tokens, jobs, backlog, Graph and Foundry are revalidated after the break.
A15 | Worker / Azure | Production rollout and operational care | Dev 2 | A14, Q14, U14 | 73 | 5 | 3 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1080 | Deploy Feb 23; observe jobs, sends, alerts and service health through Feb 26.
B01 | API / Portal | Portal shell, API contracts and API/Portal CI | Dev 1 |  | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Portal and API build/deploy pipelines run; domain contracts are agreed.
B02 | API / Portal | Okta session and resource-authorized Case API | Dev 1 | B01, A01, E01 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | User, BU, Case and source access are enforced at every API entry.
B03 | API / Portal | Case workspace, open items and offline updates | Dev 1 | B02 | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | AMs assign, update, complete and reopen work with source/history visibility.
B04 | API / Portal | Triage Create / Link / Ignore user flow | Dev 1 | B03 | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Confirmed decisions atomically update mail links and Case state.
B05 | API / Portal | Draft editing and Approve & Send API | Dev 1 | B04, A04, S04 | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Approval stores actual recipients, content and a send job atomically.
B06 | API / Portal | Draft, approval and automatic send integration | Dev 1 | B05, A06:SS, S06:SS | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | One AM approval triggers send; pending, uncertain and sent states differ.
B07 | API / Portal | Customer overview and Local / Regional views | Dev 1 | B06 | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Market completion is distinct from overall closure; source ACLs remain separate.
B08 | API / Portal | Playbook Studio and template-based data import | Dev 1 | B07, S07 | 36 | 10 | 8 | 45 | 2026-12-21 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | Prompt/examples create bounded drafts; replay and human publication work. | Dec 21–Jan 1: implementation, integrated replay and business-defect fixes.
B09 | API / Portal | API replicas, latency tracing and business fixes | Dev 1 | B08, U08 | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | API/Portal failover, session handling, tracing and business defects are verified.
B10 | API / Portal | Release candidate and AM training materials | Dev 1 | B09, S09 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Candidate UI, AM guide, failure states and source context are reviewable.
B11 | API / Portal | UAT user-story and usability fixes | Dev 1 | B10 | 56 | 5 | 4 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1440 | Core user-story defects are fixed and affected business paths retested.
B12 | API / Portal | API rollout, rollback and production configuration | Dev 1 | B11, U11 | 61 | 5 | 4 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1440 | Owner mapping, access lists, API release checks and rollback are validated.
B13 | API / Portal | Pre-holiday scope and configuration freeze | Dev 1 | B12, U12 | 66 | 2 | 1.5 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 540 | Approved scope, configuration and AM communications are frozen before leave.
B14 | API / Portal | Post-holiday API/Portal readiness and fixes | Dev 1 | B13 | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1440 | Login/session, Case mutations, approval and business views pass re-entry tests.
B15 | API / Portal | Production user-flow support and care | Dev 1 | B14, Q14, U14 | 73 | 5 | 3 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1080 | First AM actions, permissions, Case state and approval flows are monitored.
S01 | Model quality | Intent taxonomy, annotation rubric and evaluation design | DS | E02:SS | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Actionability, matching, evidence and reply quality have agreed labels.
S02 | Model quality | Corpus audit and tuning/dev/holdout split | DS | S01, U01 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Authorized de-identified threads are split by thread/Case to prevent leakage.
S03 | Model quality | Foundry baseline, schemas and starter prompts | DS | S02, A02 | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Repeatable baseline reports errors, latency and token consumption.
S04 | Model quality | Intent, Case matching and evidence extraction tuning | DS | S03, U03 | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Ambiguous identities and periods request review; dev-set replay is repeatable.
S05 | Model quality | Summary and reply prompt/template tuning | DS | S04 | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Dates, commitments, attachments and unsupported facts have adverse examples.
S06 | Model quality | End-to-end draft tuning on real test threads | DS | S05, B05 | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Live test-mail failures are classified and reproduced without holdout leakage.
S07 | Model quality | Playbook generation from prompt and sample emails | DS | S06 | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Only registered rules/schemas are generated; positive/negative replay works.
S08 | Model quality | Language, long-thread and incomplete-evidence tuning | DS | S07, U07 | 36 | 10 | 8 | 45 | 2026-12-21 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | Promise/completion, multiple intents and unread attachments are distinguished.
S09 | Model quality | Error reduction and model/prompt candidate freeze | DS | S08 | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Pin model deployment, prompts, schema, Playbooks and evaluation configuration.
S10 | Model quality | Independent holdout analysis and release decision | DS | S09, U09 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | QA runs the holdout; DS reports errors and evidence against agreed thresholds.
S11 | Model quality | UAT error analysis, latency and cost review | DS | S10 | 56 | 5 | 3 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1080 | New findings reproduce in dev data; changes trigger affected re-evaluation. | No model-weight fine-tuning is assumed.
S12 | Model quality | Final model fixes and business acceptance support | DS | S11, U11 | 61 | 5 | 3 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1080 | Accepted model/prompt candidates and fallback artifacts are traceable. | Do not tune on holdout answers.
S13 | Model quality | Pre-holiday model configuration lock | DS | S12 | 66 | 2 | 1 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 360 | Deployment and prompt settings are locked; rollback configuration is retained. | Feb 1–2 only.
S14 | Model quality | Post-holiday model regression and drift checks | DS | S13 | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1440 | Confirm deployed model behavior, critical examples, quotas, latency and cost.
S15 | Model quality | Production model quality monitoring | DS | S14, U14 | 73 | 5 | 2 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 720 | Review initial authorized samples and investigate quality/cost anomalies. | Support rollback if release criteria are violated.
Q01 | Technical QA | Test strategy, API contracts and automation scaffold | Tester 1 |  | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Permission, concurrency and failure matrices are mapped to executable tests.
Q02 | Technical QA | SSO, OAuth, renewal and authorization testing | Tester 1 | Q01, A02:SS, B02:SS | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Expiry, reconnect, denied scope and cross-user access have negative tests.
Q03 | Technical QA | Graph paging, deduplication and cursor recovery tests | Tester 1 | Q02, A03:SS | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Approved folders and Sent Items sync without skipped or duplicated work.
Q04 | Technical QA | Persistent-job lease and idempotency automation | Tester 1 | Q03, A04:SS | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Crash, duplicate claim, late response and lost-commit acknowledgements are tested.
Q05 | Technical QA | Triage, draft and scope-negative API testing | Tester 1 | Q04, A05:SS, B05:SS | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Duplicate Cases, unauthorized sources and malformed inputs are rejected.
Q06 | Technical QA | Approve-and-send integration and fault injection | Tester 1 | Q05, A06:SS, B06:SS | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Real test mailbox sends; duplicate approval and JVM loss cannot blindly resend.
Q07 | Technical QA | Send reconciliation and Outlook-human-reply tests | Tester 1 | Q06, A07:SS | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Lost responses, delayed Sent Items, NDR and uncertain outcomes have evidence.
Q08 | Technical QA | Replica, throttling and observability qualification | Tester 1 | Q07, A08:SS | 36 | 10 | 8 | 45 | 2026-12-21 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | Worker replicas and dependency timeout/rate-limit/OOM scenarios are testable.
Q09 | Technical QA | System, concurrent mutation and JVM/DB failover tests | Tester 1 | Q08, A09:SS, B09:SS | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Both services recover; stale workers fail; business writes and tasks stay consistent.
Q10 | Technical QA | Clean deploy, restore and release-candidate regression | Tester 1 | Q09, A10:SS | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Qualified artifacts deploy from clean state; critical negatives actually run in CI.
Q11 | Technical QA | UAT fix regression and security review | Tester 1 | Q10, A11:SS, B11:SS | 56 | 5 | 4 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1440 | Affected API, integration and fault paths are rechecked after fixes.
Q12 | Technical QA | Release regression and two-service rollback rehearsal | Tester 1 | Q11, A12:SS, B12:SS | 61 | 5 | 4 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1440 | P0/P1 defects are closed; approved send/recovery and rollback evidence is retained.
Q13 | Technical QA | Pre-holiday technical checkpoint | Tester 1 | Q12 | 66 | 2 | 1.5 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 540 | Frozen artifacts, alerts, backups and recovery instructions are verified.
Q14 | Technical QA | Post-holiday full regression and technical Go/No-Go | Tester 1 | Q13, A14:SS, B14:SS | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1440 | Re-run core, send, permission and recovery paths against the final release.
Q15 | Technical QA | Production smoke tests and alert verification | Tester 1 | Q14, U14 | 73 | 5 | 3 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1080 | Controlled production login, sync, Case, approval/send and alert tests pass.
U01 | Business QA | User stories, business examples and UAT recruitment | Tester 2 | E02:SS | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Frequent scenarios have approved examples, expected outcomes and AM reviewers.
U02 | Business QA | Annotation and independent holdout custody | Tester 2 | U01, S01 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Annotation consistency is sampled; final holdout remains isolated from tuning.
U03 | Business QA | Case, open items and offline progress acceptance | Tester 2 | U02, B03:SS | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Assignment, offline updates, completion/reopen and source viewing work.
U04 | Business QA | Triage, multiple Cases and manual correction tests | Tester 2 | U03, B04:SS | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Different periods, unresolved identities and multiple intents have counterexamples.
U05 | Business QA | Summary, draft edits and factual correctness checks | Tester 2 | U04, B05:SS, S05:SS | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | No invented dates, amounts, attachments or completion claims in tested cases.
U06 | Business QA | Approve-and-send business acceptance | Tester 2 | U05, B06:SS | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Recipients, content and attachments match AM approval; send status is honest.
U07 | Business QA | Regional/Local, overview and due-date acceptance | Tester 2 | U06, B07:SS | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Mail ACLs remain separate; Local completion cannot close the overall Case.
U08 | Business QA | Playbook Studio, import and business-negative testing | Tester 2 | U07, B08:SS, S08:SS | 36 | 10 | 8 | 45 | 2026-12-21 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 | AM publishes bounded rules; example emails cannot become current facts.
U09 | Business QA | Cross-scenario regression and holdout lock | Tester 2 | U08, B09:SS | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Launch scenarios and unknown/failure cases are covered; holdout inputs are locked.
U10 | Business QA | Independent holdout evaluation of frozen candidate | Tester 2 | U09, S09 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Use predefined rubric and report sample sizes, quality metrics and failure classes.
U11 | Business QA | Pilot AM UAT and training | Tester 2 | U10, B10 | 56 | 5 | 4 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1440 | Real AMs execute core stories and record blockers and usability findings.
U12 | Business QA | UAT retest and business acceptance | Tester 2 | U11, B11, S11 | 61 | 5 | 4 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 1440 | Owner accepts scope/model quality; no unresolved critical business defects.
U13 | Business QA | Pre-holiday AM sign-off and release freeze | Tester 2 | U12 | 66 | 2 | 1.5 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 540 | Pilot users, scope, mappings and pending issues are confirmed before leave.
U14 | Business QA | Post-holiday business regression and final sign-off | Tester 2 | U13, B14:SS, S14:SS | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1440 | AM flows, mappings and model-backed outputs are revalidated after the break.
U15 | Business QA | Production business checks and handover | Tester 2 | U14, Q14 | 73 | 5 | 3 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1080 | Sample initial customer cases, approved sends and owner mappings; hand over support.
E01 | External dependency | Test Azure, Okta/Entra, Graph and Foundry approvals | IT |  | 1 | 5 |  | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | EXT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Test mailboxes, model deployment/quota and resource access are ready. | External effort is not estimated or costed.
E02 | External dependency | Business scope, data use, send policy and quality targets | Business Owner |  | 1 | 5 |  | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | EXT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Approve 2–3 launch scenarios, authorized samples, owners and send boundaries. | Business decisions cannot be delegated to the DS.
E03 | External dependency | Production network, security and resource approvals | IT | E01 | 36 | 9 |  | 44 | 2026-12-21 | 2026-12-31 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | EXT | EXT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Production permissions, networking and quotas are ready by Dec 31 for preproduction. | Submit early; external support is outside the five-person estimate.
Formulas:
Start date = IF(OR([Start WD]="",[Start WD]<1,[Start WD]>Calendar!$B9),"",INDEX(Calendar!$A16:A134,MATCH([Start WD],Calendar!$D16:D134,0)))
Finish date = IF(OR([Finish WD]="",[Finish WD]<1,[Finish WD]>Calendar!$B9),"",INDEX(Calendar!$A16:A134,MATCH([Finish WD],Calendar!$D16:D134,0)))

## Team and Gates
Resource Cost, Weekly Capacity and Release Gates
Planned utilization | 80% |  | Labor cost = Gantt-scheduled person-days × daily rate. Default USD 360 per person-day. Leave and unassigned reserve are excluded.
Resource | Scheduled days | Rate (USD/day) | Cost (USD) | Available days | Reserve days | Capacity / input status
Dev 1 | 60.5 | 360 | 21780 | 77 | 16.5 | Reserve available
Dev 2 | 60.5 | 360 | 21780 | 77 | 16.5 | Reserve available
DS | 57 | 360 | 20520 | 77 | 20 | Reserve available
Tester 1 | 60.5 | 360 | 21780 | 77 | 16.5 | Reserve available
Tester 2 | 60.5 | 360 | 21780 | 77 | 16.5 | Reserve available
TOTAL | 299 |  | 107640 | 385 | 86
Weekly allocation in person-days. Available days already exclude the Calendar holidays. Enter only additional individual leave below.
Resource | Measure | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | Total | Status
|  | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22
Dev 1 | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1.5 | 0 | 4 | 3 | 60.5 | Reserve available
Dev 1 | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 77
Dev 1 | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev 1 | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 2 | 16.5
Dev 2 | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1.5 | 0 | 4 | 3 | 60.5 | Reserve available
Dev 2 | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 77
Dev 2 | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev 2 | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 2 | 16.5
DS | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1 | 0 | 4 | 2 | 57 | Reserve available
DS | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 77
DS | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 0 | 1 | 3 | 20
Tester 1 | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1.5 | 0 | 4 | 3 | 60.5 | Reserve available
Tester 1 | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 77
Tester 1 | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tester 1 | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 2 | 16.5
Tester 2 | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1.5 | 0 | 4 | 3 | 60.5 | Reserve available
Tester 2 | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 77
Tester 2 | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tester 2 | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 2 | 16.5
Responsibility split and handoffs
Dev 1 | API and Portal | 2026-11-02: Own user-facing API, front-end integration, Case/Open Items, approval and Playbook Studio. Own API/Portal CI/CD, health probes, replicas and request tracing.
Dev 2 | Worker and Azure | 2026-11-02: Own Worker, PostgreSQL, Blob, Graph, Foundry adapters, persistent jobs and sending. Own Worker CI/CD, scaling, backlog telemetry, database recovery and alerts.
DS | Model quality | 2026-11-02: Own prompts, schemas, examples, Playbook generation, model choice and error analysis. No base-model weight training is assumed.
Tester 1 | Technical QA | 2026-11-02: Own API automation, permissions, CI execution, concurrency, idempotency, crash/failover tests, sender reconciliation and rollback verification.
Tester 2 | Business and quality QA | 2026-11-02: Own user-story acceptance, annotation, holdout custody/execution, Local/Regional scenarios, UAT, training and business sign-off coordination.
Release gates: evidence and approval remain pending until executed
Gate | Milestone | 2026-11-02: Week; 2026-11-09: Review date; 2026-11-16: Owner; 2026-11-23: Evidence; 2026-11-30: Decision; 2026-12-07: Exit criteria
G1 | Identity and platform connected | 2026-11-02: 2; 2026-11-09: 2026-11-13; 2026-11-16: Dev 2; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: SSO, Graph renewal and Foundry smoke pass; denied scopes are tested.
G2 | Real-mail Triage working | 2026-11-02: 5; 2026-11-09: 2026-12-04; 2026-11-16: Dev 2; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Mail sync, explainable suggestions and human create/link/ignore complete.
G3 | Approve-and-send end to end | 2026-11-02: 6; 2026-11-09: 2026-12-11; 2026-11-16: Dev 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Real test mail reaches Case, draft, AM approval and send; duplicate approval is safe.
G4 | Launch features frozen | 2026-11-02: 9; 2026-11-09: 2027-01-01; 2026-11-16: Dev 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Launch scenarios, regional views, open items, overview and bounded Playbook Studio complete.
G5 | Independent evaluation / RC | 2026-11-02: 11; 2026-11-09: 2027-01-15; 2026-11-16: DS; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Frozen model/prompt candidate meets pre-agreed metrics on independently held-out data.
G6 | Pilot UAT accepted | 2026-11-02: 13; 2026-11-09: 2027-01-29; 2026-11-16: Tester 2; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Business owner accepts scope and model quality; critical UAT issues are closed.
G7 | Pre-holiday release checkpoint | 2026-11-02: 14; 2026-11-09: 2027-02-02; 2026-11-16: Dev 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Artifacts, configuration, backups and rollback guidance are frozen by Feb 2.
G8 | Post-holiday Go / No-Go | 2026-11-02: 16; 2026-11-09: 2027-02-19; 2026-11-16: Tester 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Full regression after leave; P0/P1 zero; permissions, sends, recovery and rollback pass.
G9 | Production release | 2026-11-02: 17; 2026-11-09: 2027-02-23; 2026-11-16: Dev 2; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Suggested Feb 23 window: controlled rollout, production smoke and recovery readiness.
G10 | Care and handover complete | 2026-11-02: 17; 2026-11-09: 2027-02-26; 2026-11-16: Dev 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Observe through Feb 26; first business records, alerts and support handover accepted.
Scope, quality criteria and planning assumptions
Scope |  | 2026-11-02: Two Java services, Next.js Portal, Graph and Foundry. Start with 2–3 frequent Playbook types and AM-approved automatic sending.
Capacity |  | 2026-11-02: 77 working days per resource after Lunar New Year leave. Plan around 80% utilization; individual extra leave reduces capacity and raises warnings.
Cost basis |  | 2026-11-02: USD 360 per scheduled person-day, editable for each person above. Task costs sum the numeric weekly Gantt allocations. Unassigned reserve and leave are not charged.
Excluded costs |  | 2026-11-02: External IT/business-owner support, Azure hosting/storage, model tokens, taxes and employer overhead are not estimated.
Workday scheduling |  | 2026-11-02: Start WD is an index in Calendar. Window WD is elapsed working time. Effort days are allocated evenly within that window; dependency checks flag manual replan needs.
Holiday changes |  | 2026-11-02: Changing shared leave dates shifts working-day-based task dates. Individual extra leave flags overload; it does not automatically reassign or move work.
External dependencies |  | 2026-11-02: E01/E02 must finish in W1. E03 must finish before preproduction. The five-person team does not absorb unestimated IT or business-owner delivery.
Evaluation |  | 2026-11-02: Start with an authorized de-identified corpus, suggested 300–500 threads. Split by thread/Case, e.g. 60% tuning, 20% dev, 20% holdout.
Quality targets |  | 2026-11-02: Confirm in W1–2: actionable recall at least 95%, matching precision at least 98%, and AM draft acceptance at least 80%. Report sample sizes and error classes.
Critical errors |  | 2026-11-02: No critical fabricated claims, wrong recipients or unauthorized disclosure in acceptance samples. This is bounded evidence, not a guarantee of zero production risk.
Model changes |  | 2026-11-02: Prompt/schema/Playbook tuning comes first. Frozen-candidate evaluation is independent; holdout answers must not become tuning data. Changes require affected re-evaluation.
Shipping controls |  | 2026-11-02: P0/P1 zero, critical negative tests executed, send idempotency/reconciliation qualified, backup/restore and rollback rehearsed, and business sign-off recorded.
Deferred |  | 2026-11-02: Deep Agents, model-weight fine-tuning, CRM write-back, AI Search, arbitrary attachment OCR, automatic Case closure and cross-region DR.
Approval UX |  | 2026-11-02: Generate draft, AM edits, Approve & Send, Worker sends automatically. Keep the actual approved payload and send job; no revision-management UI.
Shared operations |  | 2026-11-02: Dev 1 owns API/Portal CI/CD, probes, replicas and request telemetry. Dev 2 owns Worker CI/CD, scaling, database migration/recovery and integration telemetry.
Codex |  | 2026-11-02: Use coding assistance to deliver testable slices earlier. Developers still own integration/review; independent testing and quality evaluation are not reduced.
User inputs |  | 2026-11-02: Start Nov 2, 2026. Finish by Feb 26, 2027. Lunar New Year leave Feb 3–12 confirmed. Christmas/New Year weekdays are available for tasks.
Architecture |  | 2026-11-02: Source: the agreed Java API/Worker design. https://github.com/realAaronWu/aam/tree/main/docs/architecture/diagrams

## Calendar
Working Calendar and Holiday Inputs
Leave period | From | Through | Planning basis
Additional leave |  |  | Optional; inactive while blank
Lunar New Year | 2027-02-03T00:00:00.000Z | 2027-02-12T00:00:00.000Z | User-confirmed dates
Calendar weeks | 17
Available workdays | 77
Weekdays excluded | 8
Dates are inclusive. Weekends and Feb 3–12 are excluded. Christmas and New Year weekdays are available for tasks.
These are project leave assumptions, not an official public-holiday calendar. Individual extra leave is entered in Team and Gates.
Date | Day | Workday flag | Workday index | Calendar week | Day status
2026-11-02 | Mon | 1 | 1 | 1 | Working day
2026-11-03 | Tue | 1 | 2 | 1 | Working day
2026-11-04 | Wed | 1 | 3 | 1 | Working day
2026-11-05 | Thu | 1 | 4 | 1 | Working day
2026-11-06 | Fri | 1 | 5 | 1 | Working day
2026-11-07 | Sat | 0 |  | 1 | Weekend
2026-11-08 | Sun | 0 |  | 1 | Weekend
2026-11-09 | Mon | 1 | 6 | 2 | Working day
2026-11-10 | Tue | 1 | 7 | 2 | Working day
2026-11-11 | Wed | 1 | 8 | 2 | Working day
2026-11-12 | Thu | 1 | 9 | 2 | Working day
2026-11-13 | Fri | 1 | 10 | 2 | Working day
2026-11-14 | Sat | 0 |  | 2 | Weekend
2026-11-15 | Sun | 0 |  | 2 | Weekend
2026-11-16 | Mon | 1 | 11 | 3 | Working day
2026-11-17 | Tue | 1 | 12 | 3 | Working day
2026-11-18 | Wed | 1 | 13 | 3 | Working day
2026-11-19 | Thu | 1 | 14 | 3 | Working day
2026-11-20 | Fri | 1 | 15 | 3 | Working day
2026-11-21 | Sat | 0 |  | 3 | Weekend
2026-11-22 | Sun | 0 |  | 3 | Weekend
2026-11-23 | Mon | 1 | 16 | 4 | Working day
2026-11-24 | Tue | 1 | 17 | 4 | Working day
2026-11-25 | Wed | 1 | 18 | 4 | Working day
2026-11-26 | Thu | 1 | 19 | 4 | Working day
2026-11-27 | Fri | 1 | 20 | 4 | Working day
2026-11-28 | Sat | 0 |  | 4 | Weekend
2026-11-29 | Sun | 0 |  | 4 | Weekend
2026-11-30 | Mon | 1 | 21 | 5 | Working day
2026-12-01 | Tue | 1 | 22 | 5 | Working day
2026-12-02 | Wed | 1 | 23 | 5 | Working day
2026-12-03 | Thu | 1 | 24 | 5 | Working day
2026-12-04 | Fri | 1 | 25 | 5 | Working day
2026-12-05 | Sat | 0 |  | 5 | Weekend
2026-12-06 | Sun | 0 |  | 5 | Weekend
2026-12-07 | Mon | 1 | 26 | 6 | Working day
2026-12-08 | Tue | 1 | 27 | 6 | Working day
2026-12-09 | Wed | 1 | 28 | 6 | Working day
2026-12-10 | Thu | 1 | 29 | 6 | Working day
2026-12-11 | Fri | 1 | 30 | 6 | Working day
2026-12-12 | Sat | 0 |  | 6 | Weekend
2026-12-13 | Sun | 0 |  | 6 | Weekend
2026-12-14 | Mon | 1 | 31 | 7 | Working day
2026-12-15 | Tue | 1 | 32 | 7 | Working day
2026-12-16 | Wed | 1 | 33 | 7 | Working day
2026-12-17 | Thu | 1 | 34 | 7 | Working day
2026-12-18 | Fri | 1 | 35 | 7 | Working day
2026-12-19 | Sat | 0 |  | 7 | Weekend
2026-12-20 | Sun | 0 |  | 7 | Weekend
2026-12-21 | Mon | 1 | 36 | 8 | Working day
2026-12-22 | Tue | 1 | 37 | 8 | Working day
2026-12-23 | Wed | 1 | 38 | 8 | Working day
2026-12-24 | Thu | 1 | 39 | 8 | Working day
2026-12-25 | Fri | 1 | 40 | 8 | Working day
2026-12-26 | Sat | 0 |  | 8 | Weekend
2026-12-27 | Sun | 0 |  | 8 | Weekend
2026-12-28 | Mon | 1 | 41 | 9 | Working day
2026-12-29 | Tue | 1 | 42 | 9 | Working day
2026-12-30 | Wed | 1 | 43 | 9 | Working day
2026-12-31 | Thu | 1 | 44 | 9 | Working day
2027-01-01 | Fri | 1 | 45 | 9 | Working day
2027-01-02 | Sat | 0 |  | 9 | Weekend
2027-01-03 | Sun | 0 |  | 9 | Weekend
2027-01-04 | Mon | 1 | 46 | 10 | Working day
2027-01-05 | Tue | 1 | 47 | 10 | Working day
2027-01-06 | Wed | 1 | 48 | 10 | Working day
2027-01-07 | Thu | 1 | 49 | 10 | Working day
2027-01-08 | Fri | 1 | 50 | 10 | Working day
2027-01-09 | Sat | 0 |  | 10 | Weekend
2027-01-10 | Sun | 0 |  | 10 | Weekend
2027-01-11 | Mon | 1 | 51 | 11 | Working day
2027-01-12 | Tue | 1 | 52 | 11 | Working day
2027-01-13 | Wed | 1 | 53 | 11 | Working day
2027-01-14 | Thu | 1 | 54 | 11 | Working day
2027-01-15 | Fri | 1 | 55 | 11 | Working day
2027-01-16 | Sat | 0 |  | 11 | Weekend
2027-01-17 | Sun | 0 |  | 11 | Weekend
2027-01-18 | Mon | 1 | 56 | 12 | Working day
2027-01-19 | Tue | 1 | 57 | 12 | Working day
2027-01-20 | Wed | 1 | 58 | 12 | Working day
2027-01-21 | Thu | 1 | 59 | 12 | Working day
2027-01-22 | Fri | 1 | 60 | 12 | Working day
2027-01-23 | Sat | 0 |  | 12 | Weekend
2027-01-24 | Sun | 0 |  | 12 | Weekend
2027-01-25 | Mon | 1 | 61 | 13 | Working day
2027-01-26 | Tue | 1 | 62 | 13 | Working day
2027-01-27 | Wed | 1 | 63 | 13 | Working day
2027-01-28 | Thu | 1 | 64 | 13 | Working day
2027-01-29 | Fri | 1 | 65 | 13 | Working day
2027-01-30 | Sat | 0 |  | 13 | Weekend
2027-01-31 | Sun | 0 |  | 13 | Weekend
2027-02-01 | Mon | 1 | 66 | 14 | Working day
2027-02-02 | Tue | 1 | 67 | 14 | Working day
2027-02-03 | Wed | 0 |  | 14 | Lunar New Year leave
2027-02-04 | Thu | 0 |  | 14 | Lunar New Year leave
2027-02-05 | Fri | 0 |  | 14 | Lunar New Year leave
2027-02-06 | Sat | 0 |  | 14 | Lunar New Year leave
2027-02-07 | Sun | 0 |  | 14 | Lunar New Year leave
2027-02-08 | Mon | 0 |  | 15 | Lunar New Year leave
2027-02-09 | Tue | 0 |  | 15 | Lunar New Year leave
2027-02-10 | Wed | 0 |  | 15 | Lunar New Year leave
2027-02-11 | Thu | 0 |  | 15 | Lunar New Year leave
2027-02-12 | Fri | 0 |  | 15 | Lunar New Year leave
2027-02-13 | Sat | 0 |  | 15 | Weekend
2027-02-14 | Sun | 0 |  | 15 | Weekend
2027-02-15 | Mon | 1 | 68 | 16 | Working day
2027-02-16 | Tue | 1 | 69 | 16 | Working day
2027-02-17 | Wed | 1 | 70 | 16 | Working day
2027-02-18 | Thu | 1 | 71 | 16 | Working day
2027-02-19 | Fri | 1 | 72 | 16 | Working day
2027-02-20 | Sat | 0 |  | 16 | Weekend
2027-02-21 | Sun | 0 |  | 16 | Weekend
2027-02-22 | Mon | 1 | 73 | 17 | Working day
2027-02-23 | Tue | 1 | 74 | 17 | Working day
2027-02-24 | Wed | 1 | 75 | 17 | Working day
2027-02-25 | Thu | 1 | 76 | 17 | Working day
2027-02-26 | Fri | 1 | 77 | 17 | Working day
2027-02-27 | Sat | 0 |  | 17 | Weekend
2027-02-28 | Sun | 0 |  | 17 | Weekend