## Delivery Timeline
AAM Delivery Plan: FSD, Focused Coding, SIT, UAT and Launch
Start | 2026-11-02T00:00:00.000Z |  | Handover | 2027-03-05T00:00:00.000Z | Go-live | 2027-03-01T00:00:00.000Z |  |  | Plan ends | 2027-03-05 |  |  | Fits deadline
Seven roles: 2 Devs, DS, 2 Testers, BA and UI/UX (design + frontend). One Spring Boot backend with Spring AI and multiple replicas.
Preparation Nov 2–20; core coding Nov 23–Dec 18; SIT/tuning Dec 21–Jan 29; UAT Feb 15–26; launch Mar 1; handover Mar 5.
Scheduled labor | 141480 |  | Person-days | 393 | Workdays | 82 |  | per person; cost excludes unassigned reserve, Azure and model consumption.
ID | Delivery workstream | Lead | Start | Finish | W01 | W02 | W03 | W04 | W05 | W06 | W07 | W08 | W09 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
[5 empty] | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01
| Available workdays |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 5
P01 | FSD, AC and default Case definitions | BA | 2026-11-02 | 2026-11-20 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P02 | UI/UX design, prototype and signoff | UI/UX | 2026-11-02 | 2026-11-20 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P03 | GitHub Actions build / deploy / rollback | Both Devs | 2026-11-02 | 2026-11-20 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P04 | Azure, identity and job foundations | Dev 2 | 2026-11-02 | 2026-11-20 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P05 | Core Java API implementation (4 weeks) | Dev 1 | 2026-11-23 | 2026-12-18 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P06 | Async / Graph / Foundry coding (4 weeks) | Dev 2 | 2026-11-23 | 2026-12-18 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P07 | Portal page implementation (4 weeks) | UI/UX | 2026-11-23 | 2026-12-18 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P08 | Corpus, labels and model baseline | DS | 2026-11-02 | 2026-11-20 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P09 | Intent, draft and Playbook AI baseline | DS | 2026-11-23 | 2026-12-18 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P10 | Focused mail-intent tuning | DS | 2026-12-21 | 2026-12-25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P11 | Focused draft-mail tuning | DS | 2026-12-28 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P12 | Focused Playbook tuning / model freeze | DS | 2027-01-04 | 2027-01-08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P13 | SIT, tuning fixes and independent evaluation | Tester 1 | 2026-12-21 | 2027-01-29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
P14 | UAT scripts, data and environment deployment | BA | 2027-01-18 | 2027-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
P15 | UAT smoke / pre-holiday readiness checkpoint | Dev 2 | 2027-02-01 | 2027-02-02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
P16 | Post-holiday AM UAT, regression and signoff | BA | 2027-02-15 | 2027-02-26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0
P17 | Production rollout, hypercare and handover | Dev 2 | 2027-03-01 | 2027-03-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Planned milestones: evidence and formal approvals remain pending
Gate | Milestone | Coordinator | Planned date | Evidence
G01 | FSD SIGNOFF | BA | 2026-11-20 | Not run | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G02 | GitHub Actions / test environment ready | Dev 2 | 2026-11-20 | Not run | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G03 | UI/UX design SIGNOFF | UI/UX | 2026-11-20 | Not run | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G04 | Feature complete / SIT entry ready | Dev 1 | 2026-12-18 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G05 | SIT START | Tester 1 | 2026-12-21 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G06 | SIT SIGNOFF | Tester 1 | 2027-01-29 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
G07 | UAT environment READY / smoke passed | Dev 2 | 2027-02-02 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
G08 | UAT START | BA | 2027-02-15 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
G09 | UAT SIGNOFF | BA | 2027-02-26 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
G10 | Release Go / No-Go | Dev 1 | 2027-03-01 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G11 | Production release | Dev 2 | 2027-03-01 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
G12 | Hypercare / handover complete | BA | 2027-03-05 | Not run | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
SIT lasts six weeks: Dec 21–Jan 29. January also prepares the UAT environment, scripts and AM reviewers.
UAT environment deployed and smoke-tested by Feb 2; Feb 3–12 leave; formal AM UAT Feb 15–26.
Go/No-Go precedes Mar 1 production deployment. Observe and hand over by Mar 5.
Four-week feature coding window excludes preparation and later defect fixes. AI generation does not replace review or acceptance.
BA and UI/UX rates and allocations are assumptions. Cost uses Gantt-scheduled effort; unused reserve and leave are not charged.

## Task Plan
Task Ownership, Working-Day Gantt and Resource Cost
Yellow cells are editable. Gantt cells show scheduled person-days. Cost = Gantt days × each resource daily rate. EXT is unestimated external effort.
Start WD / Window WD use the working-day index. Dependencies flag manual replanning needs. Dates are plans, not signoff evidence.
ID | Workstream | Task / deliverable | Owner | Dependencies | Start WD | Window WD | Effort days | Finish WD | Start date | Finish date | Progress | Plan check | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | Cost (USD) | Acceptance / handoff evidence | Planning / risk notes
[13 empty] | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01
B01 | API / domain | GitHub Actions: Java build, unit tests and PR checks | Dev 1 |  | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
B02 | API / domain | API contracts, Okta/session scaffold and contract-test pipeline | Dev 1 | B01 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
B03 | API / domain | Backend test deployment, FSD/API review and pipeline qualification | Dev 1 | B02 | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | API contract and PR checks run in GitHub Actions; Dev 1 and Dev 2 share one Spring Boot backend deployment.
B04 | API / domain | AI-assisted coding: Case, Open Item and access-control APIs | Dev 1 | B03, BA03, F03, A03 | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
B05 | API / domain | AI-assisted coding: Triage decisions and customer dashboard APIs | Dev 1 | B04 | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
B06 | API / domain | AI-assisted coding: draft approval and Playbook authoring APIs | Dev 1 | B05 | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
B07 | API / domain | Complete API/Portal integration and developer acceptance checks | Dev 1 | B06 | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
B08 | API / domain | SIT fixes: intent/Triage behavior and authorized source context | Dev 1 | B07 | 36 | 5 | 4 | 40 | 2026-12-21 | 2026-12-25 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
B09 | API / domain | SIT fixes: draft editing, approval binding and business rules | Dev 1 | B08 | 41 | 5 | 4 | 45 | 2026-12-28 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
B10 | API / domain | SIT fixes: Playbook publication, replay and stale-edit checks | Dev 1 | B09 | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
B11 | API / domain | Release-candidate regression fixes and SIT closure evidence | Dev 1 | B10 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
B12 | API / domain | Extended SIT tuning defects and API/business-rule fixes | Dev 1 | B11 | 56 | 5 | 3 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
B13 | API / domain | SIT retests and UAT-environment configuration | Dev 1 | B12 | 61 | 5 | 3 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1080 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
B14 | API / domain | UAT deployment and API/session smoke tests | Dev 1 | B13 | 66 | 2 | 1.5 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 540 | Qualified release artifacts, operational checks and named handover evidence are recorded.
B16 | API / domain | Formal AM UAT support and bounded API defect fixes | Dev 1 | B14 | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1440 | Pilot AMs execute first-week UAT scenarios; defects and affected regression/AI retests are recorded for final acceptance on Feb 26.
B17 | API / domain | UAT API fixes, final regression and accepted release configuration | Dev 1 | B16, Q16, U16 | 73 | 5 | 3 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1080 | Final UAT evidence, controlled defect retests and business-owner approval are recorded by Feb 26.
A01 | Async / Azure | GitHub Actions: Azure OIDC, backend image and DB migration workflow | Dev 2 |  | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
A02 | Async / Azure | Test infrastructure, Graph/Foundry access and Spring AI spike | Dev 2 | A01, E01 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
A03 | Async / Azure | Environment promotion, rollback pipeline and durable-job foundation | Dev 2 | A02 | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | GitHub Actions builds one Java image, deploys test, exercises failure propagation and rollback with Azure OIDC.
A04 | Async / Azure | AI-assisted coding: mailbox delta sync, deduplication and job leases | Dev 2 | A03, BA03, F03, B03 | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
A05 | Async / Azure | AI-assisted coding: intent/Case matching and Foundry adapters | Dev 2 | A04 | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
A06 | Async / Azure | AI-assisted coding: async reply/Playbook generation and approved sending | Dev 2 | A05 | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
A07 | Async / Azure | Complete send reconciliation, replicas, observability and integrations | Dev 2 | A06 | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
A08 | Async / Azure | SIT fixes: intent jobs, lease recovery and provider throttling | Dev 2 | A07 | 36 | 5 | 4 | 40 | 2026-12-21 | 2026-12-25 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
A09 | Async / Azure | SIT fixes: draft latency, approved sends and uncertain-send recovery | Dev 2 | A08 | 41 | 5 | 4 | 45 | 2026-12-28 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
A10 | Async / Azure | SIT fixes: Playbook jobs, concurrency and bounded executor isolation | Dev 2 | A09 | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
A11 | Async / Azure | Restore, failover, clean deploy and backend rollback qualification | Dev 2 | A10 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
A12 | Async / Azure | Extended SIT integration fixes, quota/latency and recovery retests | Dev 2 | A11 | 56 | 5 | 3 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
A13 | Async / Azure | SIT closure, UAT environment deployment and rollback rehearsal | Dev 2 | A12 | 61 | 5 | 3 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1080 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
A14 | Async / Azure | UAT environment smoke, backups and pre-holiday checkpoint | Dev 2 | A13 | 66 | 2 | 1.5 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 540 | Qualified release artifacts, operational checks and named handover evidence are recorded.
A16 | Async / Azure | Formal AM UAT support and post-holiday integration checks | Dev 2 | A14 | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1440 | Pilot AMs execute first-week UAT scenarios; defects and affected regression/AI retests are recorded for final acceptance on Feb 26.
A17 | Async / Azure | UAT integration retests and final production-release rehearsal | Dev 2 | A16, Q16, U16 | 73 | 5 | 3 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1080 | Final UAT evidence, controlled defect retests and business-owner approval are recorded by Feb 26.
S01 | Model quality | Mail taxonomy, quality metrics and corpus/data-access requirements | DS |  | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Authorized corpus, leakage-safe splits, rubric and repeatable model baseline are reviewable.
S02 | Model quality | De-identification, annotation rubric and tuning/dev/holdout split | DS | S01 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Authorized corpus, leakage-safe splits, rubric and repeatable model baseline are reviewable.
S03 | Model quality | Foundry baseline and model/schema evaluation harness | DS | S02, A02, U02 | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Authorized corpus, leakage-safe splits, rubric and repeatable model baseline are reviewable.
S04 | Model quality | Functional baseline: mail intent and Case-match suggestions | DS | S03, BA03, F03, A03, B03 | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Typed outputs, prompts and examples pass functional replay; quality is not yet signed off. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
S05 | Model quality | Functional baseline: summaries and grounded reply generation | DS | S04 | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Typed outputs, prompts and examples pass functional replay; quality is not yet signed off. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
S06 | Model quality | Functional baseline: prompt/example-to-Playbook generation | DS | S05 | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Typed outputs, prompts and examples pass functional replay; quality is not yet signed off. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
S07 | Model quality | Integrated AI baseline, adverse examples and tuning backlog | DS | S06 | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Typed outputs, prompts and examples pass functional replay; quality is not yet signed off. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
S08 | Model quality | Focused tuning: mail intent, customer resolution and Case matching | DS | S07 | 36 | 5 | 4 | 40 | 2026-12-21 | 2026-12-25 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Versioned tuning/dev replay reports error classes, intent accuracy, draft acceptance and valid Playbook replay. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
S09 | Model quality | Focused tuning: draft-mail facts, recipients, tone and usefulness | DS | S08 | 41 | 5 | 4 | 45 | 2026-12-28 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Versioned tuning/dev replay reports error classes, intent accuracy, draft acceptance and valid Playbook replay. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
S10 | Model quality | Focused tuning: Playbook rules and example replay; freeze Jan 8 | DS | S09 | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Versioned tuning/dev replay reports error classes, intent accuracy, draft acceptance and valid Playbook replay. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
S11 | Model quality | Independent evaluation analysis and bounded fixes/re-evaluation | DS | S10, U10 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Tester 2 executes the independent holdout. DS analyzes results without tuning on holdout answers. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
S12 | Model quality | Extended SIT intent/draft/Playbook tuning and dev-set replay | DS | S11 | 56 | 5 | 4 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | SIT findings reproduce on dev data; changed candidates receive affected independent re-evaluation. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
S13 | Model quality | Final candidate freeze and independent re-evaluation support | DS | S12 | 61 | 5 | 4 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1440 | SIT findings reproduce on dev data; changed candidates receive affected independent re-evaluation. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
S14 | Model quality | UAT model deployment smoke and configuration lock | DS | S13 | 66 | 2 | 1 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 360 | Model, prompt, schema and Playbook versions plus quality/cost checks are recorded.
S16 | Model quality | Formal UAT AI evaluation and post-holiday model regression | DS | S14 | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1440 | Pilot AMs execute first-week UAT scenarios; defects and affected regression/AI retests are recorded for final acceptance on Feb 26.
S17 | Model quality | UAT AI-quality retests and final accepted model/prompt package | DS | S16, Q16, U16 | 73 | 5 | 3 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1080 | Final UAT evidence, controlled defect retests and business-owner approval are recorded by Feb 26.
Q01 | Technical QA | Test strategy, CI test discovery and failure-path requirements | Tester 1 |  | 1 | 5 | 3 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
Q02 | Technical QA | Review FSD AC: permissions, idempotency and integration failures | Tester 1 | Q01 | 6 | 5 | 3 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
Q03 | Technical QA | SIT plan, automation scaffold, test mailboxes and entry checklist | Tester 1 | Q02 | 11 | 5 | 3 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
Q04 | Technical QA | Continuous component/API tests: Cases, jobs and authorization | Tester 1 | Q03 | 16 | 5 | 3 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
Q05 | Technical QA | Continuous component tests: Triage, Graph sync and matching | Tester 1 | Q04 | 21 | 5 | 3 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
Q06 | Technical QA | Continuous integration checks: draft approval and send recovery | Tester 1 | Q05 | 26 | 5 | 3 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
Q07 | Technical QA | Pre-SIT smoke, test-data readiness and complete-feature handoff | Tester 1 | Q06 | 31 | 5 | 3 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
Q08 | Technical QA | SIT START: full-system integration, replicas and crash tests | Tester 1 | Q07, A07, B07, F07, S07, BA07, E03 | 36 | 5 | 4 | 40 | 2026-12-21 | 2026-12-25 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
Q09 | Technical QA | SIT: sender faults, concurrency, throttling and regression | Tester 1 | Q08 | 41 | 5 | 4 | 45 | 2026-12-28 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
Q10 | Technical QA | SIT: security, performance, restore and rollback tests | Tester 1 | Q09 | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
Q11 | Technical QA | SIT exit regression, evidence pack and signoff recommendation | Tester 1 | Q10 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
Q12 | Technical QA | Extended SIT technical fixes, failure tests and regression | Tester 1 | Q11, U11, S11, A11, B11, F11, BA11 | 56 | 5 | 4 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
Q13 | Technical QA | SIT exit regression, signoff pack and UAT deployment tests | Tester 1 | Q12 | 61 | 5 | 4 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1440 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
Q14 | Technical QA | UAT environment smoke and pre-holiday readiness checkpoint | Tester 1 | Q13 | 66 | 2 | 1.5 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 540 | Qualified release artifacts, operational checks and named handover evidence are recorded.
Q16 | Technical QA | Formal UAT support, full regression and technical exit evidence | Tester 1 | Q14 | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1440 | Pilot AMs execute first-week UAT scenarios; defects and affected regression/AI retests are recorded for final acceptance on Feb 26.
Q17 | Technical QA | Final UAT technical regression, security and rollback evidence | Tester 1 | Q16, U16 | 73 | 5 | 4 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1440 | Final UAT evidence, controlled defect retests and business-owner approval are recorded by Feb 26.
U01 | Business QA | Business test strategy and BA default-case workshops | Tester 2 |  | 1 | 5 | 3 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
U02 | Business QA | Review FSD AC and annotate authorized example threads | Tester 2 | U01 | 6 | 5 | 3 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
U03 | Business QA | Trace AC to tests; lock independent holdout custody | Tester 2 | U02 | 11 | 5 | 3 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist.
U04 | Business QA | Continuous acceptance checks: Case/Open Items and source ACLs | Tester 2 | U03 | 16 | 5 | 3 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
U05 | Business QA | Continuous acceptance checks: intent/Triage and customer views | Tester 2 | U04 | 21 | 5 | 3 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
U06 | Business QA | Continuous acceptance checks: draft facts and Playbook behavior | Tester 2 | U05 | 26 | 5 | 3 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
U07 | Business QA | Pre-SIT business walkthrough and expected-outcome checks | Tester 2 | U06 | 31 | 5 | 3 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests.
U08 | Business QA | SIT START: complete default-case journeys and intent evaluation | Tester 2 | U07, A07, B07, F07, S07, BA07, E03 | 36 | 5 | 4 | 40 | 2026-12-21 | 2026-12-25 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
U09 | Business QA | SIT: independent draft-quality evaluation and adverse examples | Tester 2 | U08 | 41 | 5 | 4 | 45 | 2026-12-28 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
U10 | Business QA | SIT: Playbook replay, cross-scenario regression and holdout lock | Tester 2 | U09 | 46 | 5 | 4 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
U11 | Business QA | Run frozen-candidate holdout; issue SIT acceptance evidence | Tester 2 | U10, S10 | 51 | 5 | 4 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
U12 | Business QA | Extended SIT business journeys and candidate-quality retests | Tester 2 | U11, Q11, S11, A11, B11, F11, BA11 | 56 | 5 | 4 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
U13 | Business QA | Independent final-candidate evaluation and SIT closure evidence | Tester 2 | U12 | 61 | 5 | 4 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1440 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality.
U14 | Business QA | UAT data/script rehearsal and basic business smoke tests | Tester 2 | U13 | 66 | 2 | 1.5 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 540 | Qualified release artifacts, operational checks and named handover evidence are recorded.
U16 | Business QA | UAT START: pilot AM execution, defect retests and signoff evidence | Tester 2 | U14 | 68 | 5 | 4 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 1440 | Pilot AMs execute first-week UAT scenarios; defects and affected regression/AI retests are recorded for final acceptance on Feb 26.
U17 | Business QA | Final AM UAT execution, defect retests and acceptance evidence | Tester 2 | U16, Q16 | 73 | 5 | 4 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1440 | Final UAT evidence, controlled defect retests and business-owner approval are recorded by Feb 26.
BA01 | FSD / business | Discover default Cases, AM journeys, scope and data ownership | BA |  | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist. | BA prepares FSD and default Cases; business owner provides formal signoff.
BA02 | FSD / business | Write FSD, per-requirement AC and default Case/Playbook templates | BA | BA01, E02 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist. | BA prepares FSD and default Cases; business owner provides formal signoff.
BA03 | FSD / business | Resolve FSD review comments; obtain FSD SIGNOFF | BA | BA02 | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Business owner signs the FSD: every requirement has AC, default Case/Playbook examples, exclusions and quality targets. | BA prepares FSD and default Cases; business owner provides formal signoff.
BA04 | FSD / business | Clarify signed FSD and Case/Open Item acceptance examples | BA | BA03 | 16 | 5 | 2 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests. BA prepares FSD and default Cases; business owner provides formal signoff.
BA05 | FSD / business | Clarify Triage, customer identity and Local/Regional scenarios | BA | BA04 | 21 | 5 | 2 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests. BA prepares FSD and default Cases; business owner provides formal signoff.
BA06 | FSD / business | Clarify reply approval and generated-Playbook acceptance rules | BA | BA05 | 26 | 5 | 2 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests. BA prepares FSD and default Cases; business owner provides formal signoff.
BA07 | FSD / business | Review complete features against signed FSD; prepare SIT handoff | BA | BA06 | 31 | 5 | 2 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests. BA prepares FSD and default Cases; business owner provides formal signoff.
BA08 | FSD / business | SIT business triage and intent-label dispute resolution | BA | BA07 | 36 | 5 | 3 | 40 | 2026-12-21 | 2026-12-25 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. BA prepares FSD and default Cases; business owner provides formal signoff.
BA09 | FSD / business | SIT draft-mail rubric decisions and factual-error review | BA | BA08 | 41 | 5 | 3 | 45 | 2026-12-28 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. BA prepares FSD and default Cases; business owner provides formal signoff.
BA10 | FSD / business | SIT Playbook rules review and UAT script preparation | BA | BA09 | 46 | 5 | 3 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. BA prepares FSD and default Cases; business owner provides formal signoff.
BA11 | FSD / business | SIT exit business review; confirm UAT entry and AM availability | BA | BA10 | 51 | 5 | 3 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. BA prepares FSD and default Cases; business owner provides formal signoff.
BA12 | FSD / business | Close SIT business gaps; prepare UAT scripts, users and data | BA | BA11, Q11, U11, S11, A11, B11, F11 | 56 | 5 | 4 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. BA prepares FSD and default Cases; business owner provides formal signoff.
BA13 | FSD / business | Coordinate SIT SIGNOFF and UAT entry/readiness review | BA | BA12 | 61 | 5 | 4 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1440 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. BA prepares FSD and default Cases; business owner provides formal signoff.
BA14 | FSD / business | Confirm UAT deployment, AM availability and February scripts | BA | BA13 | 66 | 2 | 1 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 360 | Qualified release artifacts, operational checks and named handover evidence are recorded. | BA prepares FSD and default Cases; business owner provides formal signoff.
BA16 | FSD / business | Coordinate AM UAT cycle 1 and triage acceptance defects | BA | BA14 | 68 | 5 | 3 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 1080 | Pilot AMs execute first-week UAT scenarios; defects and affected regression/AI retests are recorded for final acceptance on Feb 26. | BA prepares FSD and default Cases; business owner provides formal signoff.
BA17 | FSD / business | Obtain UAT SIGNOFF on Feb 26 and finalize business acceptance | BA | BA16, Q16, U16 | 73 | 5 | 4 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1440 | Final UAT evidence, controlled defect retests and business-owner approval are recorded by Feb 26. | BA prepares FSD and default Cases; business owner provides formal signoff.
F01 | Design / frontend | Map AM journeys and design Dashboard/Triage/Workspace wireframes | UI/UX |  | 1 | 5 | 4 | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist. | One UI/UX resource is assumed capable of frontend implementation, not design only.
F02 | Design / frontend | Design high-fidelity pages, reply/Playbook flows and error states | UI/UX | F01 | 6 | 5 | 4 | 10 | 2026-11-09 | 2026-11-13 | 0% | Scheduled | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Reviewed preparation artifact, mapped to FSD/AC and handoff checklist. | One UI/UX resource is assumed capable of frontend implementation, not design only.
F03 | Design / frontend | Prototype review, UX signoff and frontend component foundation | UI/UX | F02 | 11 | 5 | 4 | 15 | 2026-11-16 | 2026-11-20 | 0% | Scheduled | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | AM/business owner approves page flows and UI states; design and frontend handoff are ready. | One UI/UX resource is assumed capable of frontend implementation, not design only.
F04 | Design / frontend | Implement Portal: Case workspace and Open Item interactions | UI/UX | F03, BA03, A03, B03 | 16 | 5 | 4 | 20 | 2026-11-23 | 2026-11-27 | 0% | Scheduled | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests. One UI/UX resource is assumed capable of frontend implementation, not design only.
F05 | Design / frontend | Implement Portal: Triage, customer dashboard and role views | UI/UX | F04 | 21 | 5 | 4 | 25 | 2026-11-30 | 2026-12-04 | 0% | Scheduled | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests. One UI/UX resource is assumed capable of frontend implementation, not design only.
F06 | Design / frontend | Implement Portal: draft editing, approval and Playbook Studio | UI/UX | F05 | 26 | 5 | 4 | 30 | 2026-12-07 | 2026-12-11 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests. One UI/UX resource is assumed capable of frontend implementation, not design only.
F07 | Design / frontend | Complete frontend/API integration, progress polling and UI checks | UI/UX | F06 | 31 | 5 | 4 | 35 | 2026-12-14 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | Developer checks and positive/negative acceptance examples pass; review AI-generated code before handoff. | Four-week feature implementation window after FSD signoff; use Codex with developer review and continuous tests. One UI/UX resource is assumed capable of frontend implementation, not design only.
F08 | Design / frontend | SIT UI fixes: intent visibility and Triage interaction | UI/UX | F07 | 36 | 5 | 2 | 40 | 2026-12-21 | 2026-12-25 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. One UI/UX resource is assumed capable of frontend implementation, not design only.
F09 | Design / frontend | SIT UI fixes: draft edits, sending states and error recovery | UI/UX | F08 | 41 | 5 | 2 | 45 | 2026-12-28 | 2027-01-01 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. One UI/UX resource is assumed capable of frontend implementation, not design only.
F10 | Design / frontend | SIT UI fixes: Playbook preview, test results and publication | UI/UX | F09 | 46 | 5 | 2 | 50 | 2027-01-04 | 2027-01-08 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. One UI/UX resource is assumed capable of frontend implementation, not design only.
F11 | Design / frontend | SIT UX closure and user-facing release-candidate polish | UI/UX | F10 | 51 | 5 | 2 | 55 | 2027-01-11 | 2027-01-15 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | Reproducible SIT evidence, defect disposition and affected-path retesting are recorded. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. One UI/UX resource is assumed capable of frontend implementation, not design only.
F12 | Design / frontend | Extended SIT usability fixes and UAT guide preparation | UI/UX | F11 | 56 | 5 | 2 | 60 | 2027-01-18 | 2027-01-22 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. One UI/UX resource is assumed capable of frontend implementation, not design only.
F13 | Design / frontend | SIT UI acceptance and deploy Portal to UAT environment | UI/UX | F12 | 61 | 5 | 2 | 65 | 2027-01-25 | 2027-01-29 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 720 | SIT evidence, defect retests and UAT-readiness artifacts are recorded; formal AM UAT is after the holiday. | Protect extended SIT, tuning and post-holiday UAT time. If quality gates slip, reduce scope or replan; do not assume more AI coding fixes quality. One UI/UX resource is assumed capable of frontend implementation, not design only.
F14 | Design / frontend | UAT Portal smoke and pre-holiday frontend freeze | UI/UX | F13 | 66 | 2 | 1 | 67 | 2027-02-01 | 2027-02-02 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 360 | Qualified release artifacts, operational checks and named handover evidence are recorded. | One UI/UX resource is assumed capable of frontend implementation, not design only.
F16 | Design / frontend | Formal AM UAT usability support and final UI acceptance | UI/UX | F14 | 68 | 5 | 2 | 72 | 2027-02-15 | 2027-02-19 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 720 | Pilot AMs execute first-week UAT scenarios; defects and affected regression/AI retests are recorded for final acceptance on Feb 26. | One UI/UX resource is assumed capable of frontend implementation, not design only.
F17 | Design / frontend | Final UAT usability retests and accepted frontend release | UI/UX | F16, Q16, U16 | 73 | 5 | 2 | 77 | 2027-02-22 | 2027-02-26 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 720 | Final UAT evidence, controlled defect retests and business-owner approval are recorded by Feb 26. | One UI/UX resource is assumed capable of frontend implementation, not design only.
E01 | External dependency | Test Azure/Okta/Graph/Foundry access and data-use approvals | IT |  | 1 | 5 |  | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | EXT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Test mailboxes, resources, model quotas and authorized corpus access are ready. | External IT effort is not estimated or costed.
E02 | External dependency | Business scope, BA/UX staffing and signoff-owner commitment | Business Owner |  | 1 | 5 |  | 5 | 2026-11-02 | 2026-11-06 | 0% | Scheduled | EXT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Name BA, UI/UX and business approver; confirm launch Cases and AM availability. | Approver/AM effort is not estimated; BA is not a substitute for business signoff.
E03 | External dependency | Production network, security and resource approvals | IT | E01 | 16 | 20 |  | 35 | 2026-11-23 | 2026-12-18 | 0% | Scheduled | 0 | 0 | 0 | EXT | EXT | EXT | EXT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Production access, networking, permissions and quotas ready by Dec 18. | Submit early for preproduction/SIT readiness; no cost estimate for external IT.
B18 | API / domain | Production API rollout support and hypercare | Dev 1 | B17, BA17, Q17, U17 | 78 | 5 | 2 | 82 | 2027-03-01 | 2027-03-05 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 720 | Go/No-Go precedes Mar 1 production deployment; smoke, monitoring and handover evidence complete by Mar 5. | Deployment after UAT signoff. Go/No-Go before release on Mar 1; observation and handover through Mar 5.
A18 | Async / Azure | Mar 1 production deployment, operational hypercare and handover | Dev 2 | A17, BA17, Q17, U17 | 78 | 5 | 3 | 82 | 2027-03-01 | 2027-03-05 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1080 | Go/No-Go precedes Mar 1 production deployment; smoke, monitoring and handover evidence complete by Mar 5. | Deployment after UAT signoff. Go/No-Go before release on Mar 1; observation and handover through Mar 5.
S18 | Model quality | Production AI quality, latency and token-cost monitoring | DS | S17, BA17, Q17, U17 | 78 | 5 | 2 | 82 | 2027-03-01 | 2027-03-05 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 720 | Go/No-Go precedes Mar 1 production deployment; smoke, monitoring and handover evidence complete by Mar 5. | Deployment after UAT signoff. Go/No-Go before release on Mar 1; observation and handover through Mar 5.
Q18 | Technical QA | Production smoke, recovery/alert checks and defect retests | Tester 1 | Q17, BA17, U17 | 78 | 5 | 2 | 82 | 2027-03-01 | 2027-03-05 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 720 | Go/No-Go precedes Mar 1 production deployment; smoke, monitoring and handover evidence complete by Mar 5. | Deployment after UAT signoff. Go/No-Go before release on Mar 1; observation and handover through Mar 5.
U18 | Business QA | Production business verification and support handover | Tester 2 | U17, BA17, Q17 | 78 | 5 | 2 | 82 | 2027-03-01 | 2027-03-05 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 720 | Go/No-Go precedes Mar 1 production deployment; smoke, monitoring and handover evidence complete by Mar 5. | Deployment after UAT signoff. Go/No-Go before release on Mar 1; observation and handover through Mar 5.
BA18 | FSD / business | Business launch communications, training and Mar 5 handover | BA | BA17, Q17, U17 | 78 | 5 | 2 | 82 | 2027-03-01 | 2027-03-05 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 720 | Go/No-Go precedes Mar 1 production deployment; smoke, monitoring and handover evidence complete by Mar 5. | Deployment after UAT signoff. Go/No-Go before release on Mar 1; observation and handover through Mar 5.
F18 | Design / frontend | Production frontend checks and usability support | UI/UX | F17, BA17, Q17, U17 | 78 | 5 | 1 | 82 | 2027-03-01 | 2027-03-05 | 0% | Scheduled | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 360 | Go/No-Go precedes Mar 1 production deployment; smoke, monitoring and handover evidence complete by Mar 5. | Deployment after UAT signoff. Go/No-Go before release on Mar 1; observation and handover through Mar 5.
Formulas:
Start date = IF(OR([Start WD]="",[Start WD]<1,[Start WD]>Calendar!$B9),"",INDEX(Calendar!$A16:A141,MATCH([Start WD],Calendar!$D16:D141,0)))
Finish date = IF(OR([Finish WD]="",[Finish WD]<1,[Finish WD]>Calendar!$B9),"",INDEX(Calendar!$A16:A141,MATCH([Finish WD],Calendar!$D16:D141,0)))

## Team and Gates
Resource Cost, Weekly Capacity, Responsibilities and Gates
Planned utilization | 80% |  | Daily rates assume USD 360 for all seven resources. Scheduled effort, not full payroll availability, is costed.
Resource | Scheduled days | Rate (USD/day) | Cost (USD) | Available days | Reserve days | Capacity / input status
Dev 1 | 60.5 | 360 | 21780 | 82 | 21.5 | Reserve available
Dev 2 | 61.5 | 360 | 22140 | 82 | 20.5 | Reserve available
DS | 62 | 360 | 22320 | 82 | 20 | Reserve available
Tester 1 | 56.5 | 360 | 20340 | 82 | 25.5 | Reserve available
Tester 2 | 56.5 | 360 | 20340 | 82 | 25.5 | Reserve available
BA | 50 | 360 | 18000 | 82 | 32 | Reserve available
UI/UX | 46 | 360 | 16560 | 82 | 36 | Reserve available
TOTAL | 393 |  | 141480 | 574 | 181
Capacity already excludes shared leave. Enter only additional individual leave. Lower role allocation means planned part-time use, not extra headcount.
Resource | Measure | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | Total | Status
|  | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01
Dev 1 | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1.5 | 0 | 4 | 3 | 2 | 60.5 | Reserve available
Dev 1 | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 5 | 82
Dev 1 | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev 1 | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0.5 | 0 | 1 | 2 | 3 | 21.5
Dev 2 | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 1.5 | 0 | 4 | 3 | 3 | 61.5 | Reserve available
Dev 2 | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 5 | 82
Dev 2 | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dev 2 | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0.5 | 0 | 1 | 2 | 2 | 20.5
DS | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 0 | 4 | 3 | 2 | 62 | Reserve available
DS | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 5 | 82
DS | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DS | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | 3 | 20
Tester 1 | Scheduled days | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 1.5 | 0 | 4 | 4 | 2 | 56.5 | Reserve available
Tester 1 | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 5 | 82
Tester 1 | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tester 1 | Unassigned days | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 1 | 3 | 25.5
Tester 2 | Scheduled days | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 1.5 | 0 | 4 | 4 | 2 | 56.5 | Reserve available
Tester 2 | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 5 | 82
Tester 2 | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tester 2 | Unassigned days | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 1 | 3 | 25.5
BA | Scheduled days | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 4 | 4 | 1 | 0 | 3 | 4 | 2 | 50 | Reserve available
BA | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 5 | 82
BA | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BA | Unassigned days | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 2 | 1 | 3 | 32
UI/UX | Scheduled days | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 2 | 2 | 1 | 46 | Reserve available
UI/UX | Available days | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 5 | 5 | 5 | 82
UI/UX | Extra leave (input) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UI/UX | Unassigned days | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 3 | 3 | 4 | 36
Role ownership: modules in one Java backend; UI/UX owns frontend implementation
Dev 1 | API / business logic | 2026-11-02: Own APIs, sessions, authorization, Cases/Open Items, Triage decisions and approval/publication logic. Own Java PR/unit/contract checks in GitHub Actions; integrate with UI/UX.
Dev 2 | Async / Azure / platform | 2026-11-02: Own Graph/Foundry/PostgreSQL/Blob, durable jobs and approved sending. Own GitHub Actions Azure OIDC, image/deployment/migrations, replicas, runtime telemetry, restore and rollback. One shared Java backend.
DS | AI quality | 2026-11-02: Own intent, draft-mail and Playbook prompts/schemas, tuning/dev evaluation and error analysis. No model-weight training assumed. Tester 2 owns final holdout execution.
Tester 1 | Technical QA / SIT | 2026-11-02: Own API/system integration, security, concurrency, idempotency, JVM failover, restore, rollback and CI execution evidence; recommend technical SIT signoff.
Tester 2 | Business QA / evaluation | 2026-11-02: Own AC-based journey tests, annotation checks, isolated holdout custody/execution, business SIT evidence and guided AM UAT execution/retesting.
BA | FSD / Cases / acceptance | 2026-11-02: Own FSD, per-requirement AC, default Case/Playbook definitions, business rubrics and clarifications. Coordinate business-owner FSD/UAT signoff, AM availability and acceptance decisions.
UI/UX | Design + frontend delivery | 2026-11-02: Own research, page/interaction design, prototypes and frontend implementation/integration. Cover loading, polling, errors, draft approval, Playbook tests and accessibility/usability fixes.
Gate dates are plans. Evidence and business / release approvals must be recorded before stage entry.
Gate | Milestone | 2026-11-02: Week; 2026-11-09: Planned date; 2026-11-16: Coordinator; 2026-11-23: Evidence; 2026-11-30: Decision; 2026-12-07: Approver and acceptance criteria
G01 | FSD SIGNOFF | 2026-11-02: 3; 2026-11-09: 2026-11-20; 2026-11-16: BA; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Business owner approves FSD, every requirement AC, default Cases/Playbooks, exclusions and measurable AI quality criteria.
G02 | GitHub Actions / test environment ready | 2026-11-02: 3; 2026-11-09: 2026-11-20; 2026-11-16: Dev 2; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Dev leads / QA accept PR checks, one backend image, test deploy, Azure OIDC, migration and rollback evidence.
G03 | UI/UX design SIGNOFF | 2026-11-02: 3; 2026-11-09: 2026-11-20; 2026-11-16: UI/UX; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Business owner / pilot AM approve page flows, key UI states and implementation scope.
G04 | Feature complete / SIT entry ready | 2026-11-02: 7; 2026-11-09: 2026-12-18; 2026-11-16: Dev 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Dev leads + QA confirm FSD scope integrated, developer tests passed, data/environment ready and no blocking smoke defects.
G05 | SIT START | 2026-11-02: 8; 2026-11-09: 2026-12-21; 2026-11-16: Tester 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: QA lead authorizes entry after FSD/design and feature-complete gates; full-system tests use qualified environments and traceable AC.
G06 | SIT SIGNOFF | 2026-11-02: 13; 2026-11-09: 2027-01-29; 2026-11-16: Tester 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: QA lead + business owner accept technical/business SIT, final-candidate AI evaluation, no open critical defects and agreed residuals.
G07 | UAT environment READY / smoke passed | 2026-11-02: 14; 2026-11-09: 2027-02-02; 2026-11-16: Dev 2; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: By Feb 2: UAT Portal/backend/models, approved data, accounts and scripts are deployed; basic sync, Case and approved-send smoke passes.
G08 | UAT START | 2026-11-02: 16; 2026-11-09: 2027-02-15; 2026-11-16: BA; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Feb 15: business owner authorizes AM UAT after SIT signoff, environment re-entry smoke, data/scripts and reviewer availability.
G09 | UAT SIGNOFF | 2026-11-02: 17; 2026-11-09: 2027-02-26; 2026-11-16: BA; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Business owner / pilot AM accept FSD journeys, AI quality, scope and defect retests; BA records final approval by Feb 26.
G10 | Release Go / No-Go | 2026-11-02: 18; 2026-11-09: 2027-03-01; 2026-11-16: Dev 1; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Mar 1 before deployment: release owner + QA + business owner require UAT signoff, P0/P1 zero, provider readiness and rollback evidence.
G11 | Production release | 2026-11-02: 18; 2026-11-09: 2027-03-01; 2026-11-16: Dev 2; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Release owner authorizes Mar 1 deployment after Go decision; controlled smoke and rollback are staffed.
G12 | Hypercare / handover complete | 2026-11-02: 18; 2026-11-09: 2027-03-05; 2026-11-16: BA; 2026-11-23: Not run; 2026-11-30: Pending; 2026-12-07: Business/service owner accepts first records, approved sends, alerts, training and support handover by Mar 5.
Scope, assumptions, tuning uncertainty and acceptance controls
Architecture |  | 2026-11-02: One Spring Boot backend, multiple replicas, Spring AI + Foundry, Next.js Portal, PostgreSQL and Blob. HTTP handlers and bounded async executors share one application.
Staffing |  | 2026-11-02: Seven assumed resources: Dev 1, Dev 2, DS, Tester 1, Tester 2, BA and UI/UX. UI/UX includes frontend implementation. Confirm availability in W1.
Preparation |  | 2026-11-02: Nov 2–20: BA writes FSD with per-requirement AC and default Case/Playbook templates; UI/UX signs off designs; Devs qualify GitHub Actions and test foundations.
Coding window |  | 2026-11-02: Nov 23–Dec 18: four weeks for feature implementation. Codex accelerates code generation; integration, reviews, permissions, idempotency and developer tests remain required.
Tuning |  | 2026-11-02: Dec 21–Jan 8: focused intent, draft-mail and Playbook tuning. Jan 11–29: independent evaluation, further SIT tuning and final-candidate re-evaluation.
Test stages |  | 2026-11-02: Continuous component tests run during coding. Formal SIT runs Dec 21–Jan 29. UAT deployment/preparation runs Jan 18–Feb 2. Formal AM UAT and regression run Feb 15–26.
Approvals |  | 2026-11-02: Dates are planned checkpoints, not approvals. BA prepares FSD/UAT evidence; named business owners approve. SIT signoff requires QA and business acceptance.
Default Cases |  | 2026-11-02: BA defines 2–3 launch templates, e.g. renewal, periodic report and program change: intent, required inputs, Case/Open Items, owners, completion evidence, replies and exceptions.
AC coverage |  | 2026-11-02: Every FSD requirement includes positive/negative AC, source permissions, failure/ambiguity behavior and expected UI states. Map AC IDs to SIT/UAT tests and evidence.
Capacity |  | 2026-11-02: 82 available workdays per person before individual leave. Most weeks allocate at most 80%; unassigned capacity handles review, defects and uncertainty. Reserve is not pre-charged.
Cost basis |  | 2026-11-02: Default USD 360 per scheduled person-day for all seven resources; edit individual rates above. Cost derives from weekly Gantt allocations. Excludes Azure, model usage, external IT/AM time and overhead.
Scheduling |  | 2026-11-02: Start WD and Window WD drive dates and weekly allocation. Extra individual leave flags capacity issues; dependencies are checked but not automatically moved or resource-leveled.
Risk response |  | 2026-11-02: Post-holiday formal UAT has ten workdays. Pre-book AM reviewers and prepare scripts/data before leave. Material late defects require approved scope/date changes; do not silently waive acceptance.
Data and eval |  | 2026-11-02: Obtain authorized de-identified examples early. Split by thread/Case before tuning. DS uses tuning/dev data; Tester 2 controls and executes independent holdout.
AI acceptance |  | 2026-11-02: Agree measurable intent recall/matching precision, grounded draft usefulness, valid Playbook/replay criteria, latency/cost and slice sample sizes at FSD signoff.
Safety |  | 2026-11-02: No critical unauthorized disclosure, wrong recipients or fabricated commitments in acceptance evidence. Sending requires AM approval; uncertain sends are reconciled, never blindly resent.
Candidate changes |  | 2026-11-02: Pin model, prompts, schema, Playbook and corpus versions. Fixes after candidate freeze/SIT signoff trigger affected regression and independent evaluation before UAT acceptance.
GitHub Actions |  | 2026-11-02: Dev 1: Java build/unit/contract PR checks. Dev 2: Azure OIDC, images, DB migration and environment deploy/rollback. UI/UX supplies frontend checks; Tester 1 verifies failure propagation.
Holiday inputs |  | 2026-11-02: Nov 2, 2026 start; Feb 26, 2027 UAT signoff; Mar 1 launch; Mar 5 handover. Feb 3–12 leave is excluded. Christmas/New Year weekdays remain available; confirm external IT/AM availability.
Launch scope |  | 2026-11-02: Mail visibility, Triage, Cases/Open Items, summaries, generated replies with AM-approved sending and bounded prompt/example-generated Playbooks. Defer autonomous multi-agent execution.

## Calendar
Working Calendar and Shared Leave
Leave period | From | Through | Planning basis
Additional leave |  |  | Optional; inactive while blank
Lunar New Year | 2027-02-03T00:00:00.000Z | 2027-02-12T00:00:00.000Z | User-confirmed dates
Calendar weeks | 18
Available workdays | 82
Weekdays excluded | 8
Weekends and Feb 3–12 are excluded. Christmas and New Year weekdays are available. Individual extra leave is entered in Team and Gates.
Dates are inclusive. UAT ends Feb 26; production starts Mar 1; observation and handover end Mar 5.
Date | Day | Workday flag | Workday index | Calendar week | Day status
2026-11-02 | Mon | 1 | 1 | 1 | Working day
2026-11-03 | Tue | 1 | 2 | 1 | Working day
2026-11-04 | Wed | 1 | 3 | 1 | Working day
2026-11-05 | Thu | 1 | 4 | 1 | Working day
2026-11-06 | Fri | 1 | 5 | 1 | Working day
2026-11-07 | Sat | 0 |  | 1 | Weekend
2026-11-08 | Sun | 0 |  | 1 | Weekend
2026-11-09 | Mon | 1 | 6 | 2 | Working day
2026-11-10 | Tue | 1 | 7 | 2 | Working day
2026-11-11 | Wed | 1 | 8 | 2 | Working day
2026-11-12 | Thu | 1 | 9 | 2 | Working day
2026-11-13 | Fri | 1 | 10 | 2 | Working day
2026-11-14 | Sat | 0 |  | 2 | Weekend
2026-11-15 | Sun | 0 |  | 2 | Weekend
2026-11-16 | Mon | 1 | 11 | 3 | Working day
2026-11-17 | Tue | 1 | 12 | 3 | Working day
2026-11-18 | Wed | 1 | 13 | 3 | Working day
2026-11-19 | Thu | 1 | 14 | 3 | Working day
2026-11-20 | Fri | 1 | 15 | 3 | Working day
2026-11-21 | Sat | 0 |  | 3 | Weekend
2026-11-22 | Sun | 0 |  | 3 | Weekend
2026-11-23 | Mon | 1 | 16 | 4 | Working day
2026-11-24 | Tue | 1 | 17 | 4 | Working day
2026-11-25 | Wed | 1 | 18 | 4 | Working day
2026-11-26 | Thu | 1 | 19 | 4 | Working day
2026-11-27 | Fri | 1 | 20 | 4 | Working day
2026-11-28 | Sat | 0 |  | 4 | Weekend
2026-11-29 | Sun | 0 |  | 4 | Weekend
2026-11-30 | Mon | 1 | 21 | 5 | Working day
2026-12-01 | Tue | 1 | 22 | 5 | Working day
2026-12-02 | Wed | 1 | 23 | 5 | Working day
2026-12-03 | Thu | 1 | 24 | 5 | Working day
2026-12-04 | Fri | 1 | 25 | 5 | Working day
2026-12-05 | Sat | 0 |  | 5 | Weekend
2026-12-06 | Sun | 0 |  | 5 | Weekend
2026-12-07 | Mon | 1 | 26 | 6 | Working day
2026-12-08 | Tue | 1 | 27 | 6 | Working day
2026-12-09 | Wed | 1 | 28 | 6 | Working day
2026-12-10 | Thu | 1 | 29 | 6 | Working day
2026-12-11 | Fri | 1 | 30 | 6 | Working day
2026-12-12 | Sat | 0 |  | 6 | Weekend
2026-12-13 | Sun | 0 |  | 6 | Weekend
2026-12-14 | Mon | 1 | 31 | 7 | Working day
2026-12-15 | Tue | 1 | 32 | 7 | Working day
2026-12-16 | Wed | 1 | 33 | 7 | Working day
2026-12-17 | Thu | 1 | 34 | 7 | Working day
2026-12-18 | Fri | 1 | 35 | 7 | Working day
2026-12-19 | Sat | 0 |  | 7 | Weekend
2026-12-20 | Sun | 0 |  | 7 | Weekend
2026-12-21 | Mon | 1 | 36 | 8 | Working day
2026-12-22 | Tue | 1 | 37 | 8 | Working day
2026-12-23 | Wed | 1 | 38 | 8 | Working day
2026-12-24 | Thu | 1 | 39 | 8 | Working day
2026-12-25 | Fri | 1 | 40 | 8 | Working day
2026-12-26 | Sat | 0 |  | 8 | Weekend
2026-12-27 | Sun | 0 |  | 8 | Weekend
2026-12-28 | Mon | 1 | 41 | 9 | Working day
2026-12-29 | Tue | 1 | 42 | 9 | Working day
2026-12-30 | Wed | 1 | 43 | 9 | Working day
2026-12-31 | Thu | 1 | 44 | 9 | Working day
2027-01-01 | Fri | 1 | 45 | 9 | Working day
2027-01-02 | Sat | 0 |  | 9 | Weekend
2027-01-03 | Sun | 0 |  | 9 | Weekend
2027-01-04 | Mon | 1 | 46 | 10 | Working day
2027-01-05 | Tue | 1 | 47 | 10 | Working day
2027-01-06 | Wed | 1 | 48 | 10 | Working day
2027-01-07 | Thu | 1 | 49 | 10 | Working day
2027-01-08 | Fri | 1 | 50 | 10 | Working day
2027-01-09 | Sat | 0 |  | 10 | Weekend
2027-01-10 | Sun | 0 |  | 10 | Weekend
2027-01-11 | Mon | 1 | 51 | 11 | Working day
2027-01-12 | Tue | 1 | 52 | 11 | Working day
2027-01-13 | Wed | 1 | 53 | 11 | Working day
2027-01-14 | Thu | 1 | 54 | 11 | Working day
2027-01-15 | Fri | 1 | 55 | 11 | Working day
2027-01-16 | Sat | 0 |  | 11 | Weekend
2027-01-17 | Sun | 0 |  | 11 | Weekend
2027-01-18 | Mon | 1 | 56 | 12 | Working day
2027-01-19 | Tue | 1 | 57 | 12 | Working day
2027-01-20 | Wed | 1 | 58 | 12 | Working day
2027-01-21 | Thu | 1 | 59 | 12 | Working day
2027-01-22 | Fri | 1 | 60 | 12 | Working day
2027-01-23 | Sat | 0 |  | 12 | Weekend
2027-01-24 | Sun | 0 |  | 12 | Weekend
2027-01-25 | Mon | 1 | 61 | 13 | Working day
2027-01-26 | Tue | 1 | 62 | 13 | Working day
2027-01-27 | Wed | 1 | 63 | 13 | Working day
2027-01-28 | Thu | 1 | 64 | 13 | Working day
2027-01-29 | Fri | 1 | 65 | 13 | Working day
2027-01-30 | Sat | 0 |  | 13 | Weekend
2027-01-31 | Sun | 0 |  | 13 | Weekend
2027-02-01 | Mon | 1 | 66 | 14 | Working day
2027-02-02 | Tue | 1 | 67 | 14 | Working day
2027-02-03 | Wed | 0 |  | 14 | Lunar New Year leave
2027-02-04 | Thu | 0 |  | 14 | Lunar New Year leave
2027-02-05 | Fri | 0 |  | 14 | Lunar New Year leave
2027-02-06 | Sat | 0 |  | 14 | Lunar New Year leave
2027-02-07 | Sun | 0 |  | 14 | Lunar New Year leave
2027-02-08 | Mon | 0 |  | 15 | Lunar New Year leave
2027-02-09 | Tue | 0 |  | 15 | Lunar New Year leave
2027-02-10 | Wed | 0 |  | 15 | Lunar New Year leave
2027-02-11 | Thu | 0 |  | 15 | Lunar New Year leave
2027-02-12 | Fri | 0 |  | 15 | Lunar New Year leave
2027-02-13 | Sat | 0 |  | 15 | Weekend
2027-02-14 | Sun | 0 |  | 15 | Weekend
2027-02-15 | Mon | 1 | 68 | 16 | Working day
2027-02-16 | Tue | 1 | 69 | 16 | Working day
2027-02-17 | Wed | 1 | 70 | 16 | Working day
2027-02-18 | Thu | 1 | 71 | 16 | Working day
2027-02-19 | Fri | 1 | 72 | 16 | Working day
2027-02-20 | Sat | 0 |  | 16 | Weekend
2027-02-21 | Sun | 0 |  | 16 | Weekend
2027-02-22 | Mon | 1 | 73 | 17 | Working day
2027-02-23 | Tue | 1 | 74 | 17 | Working day
2027-02-24 | Wed | 1 | 75 | 17 | Working day
2027-02-25 | Thu | 1 | 76 | 17 | Working day
2027-02-26 | Fri | 1 | 77 | 17 | Working day
2027-02-27 | Sat | 0 |  | 17 | Weekend
2027-02-28 | Sun | 0 |  | 17 | Weekend
2027-03-01 | Mon | 1 | 78 | 18 | Working day
2027-03-02 | Tue | 1 | 79 | 18 | Working day
2027-03-03 | Wed | 1 | 80 | 18 | Working day
2027-03-04 | Thu | 1 | 81 | 18 | Working day
2027-03-05 | Fri | 1 | 82 | 18 | Working day
2027-03-06 | Sat | 0 |  | 18 | Weekend
2027-03-07 | Sun | 0 |  | 18 | Weekend